## Pipette
No | PCB | Version | Issue Date | Closed Date | Status | Request | Response
1 | Pipette | V1.0 | 2018-04-03 | 2018-04-16 | Closed | S/V 구매 - Series LX-Value_8mm | X-Valve 구매 - X605SF
2 | Pipette | V1.0 | 2018-04-03 |  | OPEN | S/V 부자재 구매 - Gasket, 12'' Wire lead, Screw | [5/17 Femto] - Connector 구매 후 전달 예정
3 | Pipette | V1.0 | 2018-04-03 |  | OPEN | Fitting 선정 및 구매
4 | Pipette | V1.0 | 2018-04-03 |  | OPEN | Needle 선정 및 구매
5 | Pipette | V1.0 | 2018-04-03 |  | OPEN | GND 판과의 연결 방법 협의
6 | Pipette | V1.0 | 2018-05-16 |  | OPEN | Battery size 확정 - 디자인 업체 inform 필요 | [5/17 Femto] - M/E 업체에 확인 후 confirm 예정
7 | Pipette | V1.0 | 2018-05-16 |  | OPEN | Battery Connector 디자인 적용 여부 확인 필요 - 부품 : 824-22-003-00-005000 | [5/17 Femto] - M/E 업체에 확인 후 confirm 예정
8 | Transformer | V2.0 | 2018-05-16 |  | Closed | Transformer 부품 - 10ea | [5/17 Femto] - No molding 8ea 입고
9 | Transformer | V2.0 | 2018-05-23 |  | OPEN | Molding된 Transformer 요청 - 각 2ea씩
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## LF Gen
No | PCB | Version | Issue Date | Closed Date | Status | Request | Response
1 | Touch PC | New | 2018-05-16 |  | OPEN | Program UI image 전달
2 | Touch PC | Old | 2018-05-16 | 2018-05-17 | Closed | 기존 LF Generator Power별로 Program 구별 방법? 1) Generator Power별로 구별하여 Program install 2) Generator MCU F/W를 구별하여 F/W download | Touch Program으로 구별 - 각 power별 개별 Program이 있음 : 입력에서 제한을 둠
3 | Touch PC | New | 2018-05-16 |  | OPEN | Touch PC OS 변경 : 기존 : CWV2-070BR(Win CE Pro embedded) New : CPCV5-070WR(Windows 10 Iot Enterprise) => 기구물 변경 필요 | [5/17 Femto] - 내부 검토 후 confirm
4 | Touch PC | Old | 2018-05-16 | 2018-05-16 | Closed | Femto 최종 version 정보 필요 - 이후 Version으로 할당 예정 | V2.0
5 | Gen Main | Old | 2018-05-16 | 2018-05-16 | Closed | Femto 최종 version 정보 필요 - 이후 Version으로 할당 예정 | V1.52
6 | Gen MCU | Old | 2018-05-16 | 2018-05-16 | Pending | Femto 최종 version 정보 필요 - 이후 Version으로 할당 예정 | 확인 불가
7 | Control Main | Old | 2018-05-16 | 2018-05-16 | Closed | Femto 최종 version 정보 필요 - 이후 Version으로 할당 예정 | V1.1
8 | Control MCU | Old | 2018-05-16 | 2018-05-16 | Pending | Femto 최종 version 정보 필요 - 이후 Version으로 할당 예정 | 확인 불가
9 | Gen Main | Old | 2018-05-23 |  | OPEN | Gen Main 부품 요청 - 5ea 기준 Gen Main bare PCB 요청 - 2ea
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26